{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Offene Punkte Liste","Standardprojektplan SW-Einführ.","Optimierung Prozess-IT-Kosten"],"not_rendered":{"defined_names":5},"read":"whole","date_system":"1900"}

{"sheet":"Offene Punkte Liste","index":0,"n_rows":106,"n_cols":15,"rows_kept":106}
[{"$nulls":14},"erledigt"]
[null,"OP-Liste xy",{"$nulls":5},{"$f":"NOW()","v":"2014-12-29T12:27:39.620"},{"$nulls":6},"läuft"]
[{"$nulls":14},"kritisch"]
[{"$nulls":14},"überfällig"]
[{"$f":"MAXA(A8:A65540)+1","v":{"v":3,"d":"3 "}},"neu zu vergebene ID",{"$nulls":12},"Beschluss"]
["ID","Tasks und Aufgaben\nProblem, Thema, Angelegenheit","Prio","Start","Ende","Aufwand","Ressource\nVerantwortlicher","Verlauf der Notizen: \nGründe, Konsequenzen (Zeit, Kosten, Ressourcen, Risiken), korrigierende Maßnahmen, Lösung","Verlauf: \nDatum & Person der Einträge …","Zeitpunkt der voraussichtl. Erledigung","Status",{"$nulls":3},"Idee"]
[]
[{"v":1,"d":"1 "},"Neues Berichtslayout Vertriebscontrolling",3,"2014-01-01","2014-01-31","30 Std.","Meyer",{"$nulls":3},"überfällig"]
[{"v":2,"d":"2 "},"Druckereinzug im Warenausgang klemmt",1,null,"2014-02-23","4 Std.","Gäbele","Beschädigung, Lieferscheine & Lieferungen gehen nicht rechtzeitig raus, Kunde verärgert, Ersatzdrucker wird aufgestellt","\n\n22.2.2014, Brösel",null,"kritisch"]
{"$rows_empty":96}
[{"$nulls":10},"x"]

{"sheet":"Standardprojektplan SW-Einführ.","index":1,"n_rows":103,"n_cols":17,"rows_kept":103}
[{"$nulls":16},"erledigt"]
["Projektplan und Aufgabenliste",{"$nulls":8},{"$f":"NOW()","v":"2014-12-29T12:27:39.620"},{"$nulls":6},"läuft"]
[{"$nulls":16},"kritisch"]
[{"$nulls":16},"überfällig"]
[{"$nulls":16},"Beschluss"]
["Phase","intern / extern","ID","Tasks und Aufgaben\nProblem, Thema, Angelegenheit","Start","Ende","Dauer","Ressource","Prozess-anweisung für ","Verlauf der Notizen: \nGründe, Konsequenzen (Zeit, Kosten, Ressourcen, Risiken), korrigierende Maßnahmen, Lösung","Verlauf: \nDatum & Person der Einträge …","Zeitpunkt der voraussichtl. Erledigung","Status",{"$nulls":3},"Idee"]
["Projektevaluierung","intern","1.1"]
["Projektevaluierung","intern","1.2"]
["Projektevaluierung","intern","1.3"]
["Projektevaluierung","intern","1.4"]
["Projektevaluierung","intern","1.5"]
["Meilenstein 1",null,"1.99","Projektentscheidung"]
["Grobkonzept Geschäftsprozesse","intern","2.1"]
["Grobkonzept Geschäftsprozesse","intern","2.2"]
["Grobkonzept Geschäftsprozesse","intern","2.3"]
["Grobkonzept Geschäftsprozesse","intern","2.4"]
["Grobkonzept Geschäftsprozesse","intern","2.5"]
["Meilenstein 2",null,"2.99","Projektentscheidung"]
["Feinkonzept Geschäftsprozesse","intern","3.1"]
["Feinkonzept Geschäftsprozesse","intern","3.2"]
["Feinkonzept Geschäftsprozesse","intern","3.3"]
["Feinkonzept Geschäftsprozesse","intern","3.4"]
["Feinkonzept Geschäftsprozesse","intern","3.5"]
["Meilenstein 3",null,"3.99"]
["DV-Grobkonzept","extern","4.1"]
["DV-Grobkonzept","extern","4.2"]
["DV-Grobkonzept","extern","4.3"]
["DV-Grobkonzept","extern","4.4"]
["DV-Grobkonzept","extern","4.5"]
["Meilenstein 4",null,"4.99","Lastenheft, Abnahme"]
["DV-Feinkonzept","extern","5.1"]
["DV-Feinkonzept","extern","5.2"]
["DV-Feinkonzept","extern","5.3"]
["DV-Feinkonzept","extern","5.4"]
["DV-Feinkonzept","extern","5.5"]
["Meilenstein 5",null,"5.99"]
["Implementierung","extern","6.1"]
["Implementierung","extern","6.2"]
["Implementierung","extern","6.3"]
["Implementierung","extern","6.4"]
["Implementierung","extern","6.5"]
["Meilenstein 5",null,"6.99"]
["Test","intern / extern","7.1"]
["Test","intern / extern","7.2"]
["Test","intern / extern","7.3"]
["Test","intern / extern","7.4"]
["Test","intern / extern","7.5"]
["Meilenstein 6",null,"7.99","Abnahme"]
["Training / IT-Doku","intern / extern","8.1"]
["Training / IT-Doku","intern / extern","8.2"]
["Training / IT-Doku","intern / extern","8.3"]
["Training / IT-Doku","intern / extern","8.4"]
["Training / IT-Doku","intern / extern","8.5"]
["Meilenstein 7",null,"8.99","Migration"]
["Wartung, Optimierung","intern / extern","9.1"]
["Wartung, Optimierung","intern / extern","9.2"]
["Wartung, Optimierung","intern / extern","9.3"]
["Wartung, Optimierung","intern / extern","9.4"]
["Wartung, Optimierung","intern / extern","9.5"]
{"$rows_empty":43}
[{"$nulls":12},"x"]

{"sheet":"Optimierung Prozess-IT-Kosten","index":2,"n_rows":107,"n_cols":23,"rows_kept":107}
[{"$f":"MAXA(A3:A65536)+1","v":5},"neu zu vergebene ID",{"$nulls":3},"Prozessoptimierung und Kostensenkungen"]
[{"$nulls":5},"Prios:",1,2,3,null,"Evaluierung","angemeldet","spezifiziert","beauftragt","qualitätsgesichert","TEST","abgenommen","reklamiert","erweitert","gestorben","angefangen","erledigt","kritisch"]
["ID","UID","Prio","Abteilung","SQL","Task","Spezifikation","Anforderer","beantragt am","Zieldatum","Zu tun","Verantwortl.\nUmsetzer","Problem","fällig","voraussichtl.\nEndtermin","erledigt","Status"]
[1,null,1,{"$nulls":12},"angefangen","Evaluierung"]
[2,null,2,{"$nulls":12},"erledigt","angemeldet"]
[3,null,3,{"$nulls":12},"kritisch","spezifiziert"]
[4,{"$nulls":15},"beauftragt"]
[{"$nulls":16},"qualitätsgesichert"]
[{"$nulls":16},"TEST"]
[{"$nulls":16},"abgenommen"]
[{"$nulls":16},"reklamiert"]
{"$rows_empty":95}
[null,null,"x",{"$nulls":12},"x"]